## Plan
ID | Task | Owner | After | Also after | Days | Start | Finish | % Done | Status
1 | Site survey | Ana |  |  | 2 |  |  | 100%
2 | Design sign-off | Ben | 1 |  | 3 |  |  | 100%
3 | Council permit | Ben | 2 |  | 10 |  |  | 100%
4 | Order equipment | Ana | 2 |  | 1 |  |  | 100%
5 | Equipment lead time | Ana | 4 |  | 28 |  |  | 0%
6 | Strip out | Chris | 3 |  | 3 |  |  | 100%
7 | Electrics rough-in | Dina | 6 |  | 4 |  |  | 75%
8 | Plumbing | Dina | 7 |  | 3 |  |  | 30%
9 | Flooring | Chris | 8 |  | 2 |  |  | 0%
10 | Paint and finish | Chris | 9 |  | 3 |  |  | 0%
11 | Install equipment | Ana | 10 | 5 | 3 |  |  | 0%
12 | Final inspection | Ben | 11 |  | 1 |  |  | 0%

## Dashboard
Inputs |  | Where the job actually stands
Project start | 2026-09-07 | Planned finish
Status date | 2026-10-08 | Working days in plan
Working days gone
Holidays |  | Schedule elapsed
2026-10-12 |  | Work complete
2026-11-11 |  | Ahead / behind
Tasks late
Unweighted average